## About
MOVE78
Shadow AI Discovery Workbook
Free Artifact - Move78 International
Purpose
A workbook for discovering unmanaged AI tool use across departments, browser extensions, copilots, AI-enabled SaaS features, informal workflows, and unsanctioned data entry.
How to use this artifact
1. Start with the highest-level register or screening sheet.
2. Replace sample rows with your own systems, vendors, incidents, or decisions.
3. Assign named owners and due dates before using the workbook as evidence.
4. Escalate legal, privacy, safety, employment, financial, or consumer-impact questions to qualified counsel.
5. Treat this as an implementation starter, not as legal advice, certification, or an audit opinion.
Publisher
Move78 International Limited Website: https://move78int.com Support: https://move78int.com/support.html Generated: 2026-04-27
#VALUE!

## Department Discovery
Department | Interview owner | Known approved AI tools | Suspected unapproved tools | Main workflow using AI | Data entered into AI tools | Policy awareness level | Discovery priority | Notes
Sales | VP Sales Ops | CRM AI assistant | Public chatbots for proposal drafting | Drafting emails and proposals | Customer names, deal information | Medium | High | Sample row
Engineering | Engineering Manager | Code assistant | Local agents and browser plugins | Code generation, debugging | Source code, logs, credentials risk | High | High | Sample row
HR | HR Business Partner | None formally approved | Resume ranking tools | Candidate screening | Applicant PII | Low | High | Sample row

## AI Tool Inventory Starter
Tool ID | Tool name | Approved? | Department using it | User group | Access method | Data sensitivity | Business criticality | Owner | Next action
AI-001 | Public chatbot used for proposal drafts | No | Sales | Account executives | Browser | Commercial confidential | Medium | VP Sales Ops | Assess and either approve with controls or block
AI-002 | Local OpenClaw agent PoC | Unknown | Engineering | Dev team | Local install / repo | Source code and logs | High | Engineering Manager | Run OpenClaw security readiness assessment
AI-003 | AI meeting summarizer | Yes | Operations | Management team | SaaS | Meeting notes | Medium | COO | Confirm retention and DPA

## Data Exposure Interview Guide
Question ID | Interview question | Why this matters | Response | Risk indicator | Follow-up action
Q-01 | Do staff paste customer, employee, source code, contract, or financial data into public AI tools? | This identifies direct leakage exposure and policy gaps. |  | High if yes or unknown | Document examples and assign remediation owner
Q-02 | Which AI browser extensions or plugins are installed on managed and unmanaged devices? | Extensions can bypass formal procurement and monitoring. |  | Medium to high if unmanaged | Review browser inventory and block risky extensions
Q-03 | Do teams use personal AI accounts for work tasks? | Personal accounts undermine enterprise logging, retention, and contractual protections. |  | High if yes | Route to approved enterprise tools or block use
Q-04 | Can managers list all AI tools used in their department? | Inventory quality is the baseline for governance evidence. |  | High if no | Create usage-based inventory and review cadence

## Browser Plugin Extension Check
Extension / plugin | Browser | Department | Approved? | Permissions observed | Data exposure risk | Owner | Action | Evidence location
AI writing assistant extension | Chrome | Sales | No | Read and change data on all websites | High | IT Security | Review and block or approve with controls | Endpoint management export
Code assistant plugin | VS Code | Engineering | Unknown | Repository access | High | Engineering Manager | Review and restrict to approved repositories | Developer workstation review

## Remediation Priority Scoring
Issue ID | Issue description | Likelihood (1-5) | Impact (1-5) | Control maturity (1-5) | Priority score | Recommended treatment | Owner | Due date | Status
ISS-001 | Sales staff use public chatbots with customer proposal content | 4 | 4 | 2 | 20 | Block sensitive data entry and provide approved alternative | VP Sales Ops | 2026-05-20 | In progress
ISS-002 | Engineering uses local agent PoC with source code access | 3 | 5 | 2 | 19 | Assess OpenClaw deployment and enforce least privilege | Engineering Manager | 2026-05-15 | Not started
ISS-003 | Browser AI extensions not centrally inventoried | 4 | 3 | 1 | 17 | Export extension inventory and block high-risk extensions | IT Security | 2026-05-10 | Not started

## Owner Action Tracker
Action ID | Related issue | Action | Owner | Priority | Due date | Status | Evidence retained? | Notes
ACT-001 | ISS-001 | Publish sensitive-data AI use restriction and approved tool path | VP Sales Ops | High | 2026-05-20 | In progress | No
ACT-002 | ISS-002 | Run OpenClaw readiness check and restrict local agents | Engineering Manager | High | 2026-05-15 | Not started | No

## Sources & Legal
Sources referenced
Source | URL
Colorado SB24-205 Consumer Protections for Artificial Intelligence | https://leg.colorado.gov/bills/sb24-205
NIST AI Risk Management Framework 1.0 | https://www.nist.gov/publications/artificial-intelligence-risk-management-framework-ai-rmf-10
NIST AI RMF Playbook and resources | https://www.nist.gov/itl/ai-risk-management-framework
NIST AI RMF Generative AI Profile | https://www.nist.gov/publications/artificial-intelligence-risk-management-framework-generative-artificial-intelligence
ISO/IEC 42001:2023 information page | https://www.iso.org/standard/81230.html
OWASP Top 10 for Large Language Model Applications | https://owasp.org/www-project-top-10-for-large-language-model-applications/

## Disclaimer & Legal
Disclaimer & Legal Notice
Informational use only
This artifact is provided for informational and educational purposes only. It does not constitute legal, regulatory, compliance, security, tax, or professional advice.
No compliance determination
Using this artifact does not establish compliance with Colorado SB24-205, ISO/IEC 42001, NIST AI RMF, EU AI Act, any privacy law, or any contractual requirement.
Local validation required
Your organization should validate all decisions with qualified legal, privacy, cybersecurity, and compliance professionals before relying on this artifact.
No warranty
The artifact is provided as-is without warranty of completeness, fitness for a particular purpose, or regulatory outcome.
Suggested use
Use this artifact to structure internal discussions, collect evidence, and identify next implementation steps. It is not an audit report or certification document.